## Sheet1
Domain | AV; Roundabout; Inters.Manag. (IM);
Scope | Safety / Efficient / Scalable IM soft
Problem | Crashes / Delay / Congestion Intersection |  | Term | Autum | [9 empty] | Holiday |  |  |  |  | Spring | [9 empty] | Holiday |  |  |  | Summer
Method | Waterfall and Agile, Gantt Planning |  | Week | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10
Model | Extend AIM4 for roundabout |  | September |  | Octomber |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  | February |  |  |  | March |  |  | March |  | April |  | April |  | May |  |  |  |  | June
Tool | GitHub, Overleaf/LaTeX, GeoGebra, Excel |  | 2017-09-25 | [10 empty] | 2017-12-01 |  | 2018-01-08 | [12 empty] | 2017-03-16 |  | 2018-04-16 |  |  |  | 2018-05-02 | [5 empty] | 2018-06-22
Remark | Role | Activity / Tasks | Duration | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w31 | w32 | w33 | w34 | w35 | w36 | w37 | w38 | w39
Doc Resercher |  | Literature Research | 6 w | Literature Research
For context |  | Broad Issues (context) | 4 w | Broad Issues (context)
Approach to problem |  | Typical Approaches | 4 w | Typical Approaches
Overlap / Inform Us |  | Studies | 4 w | Studies
Strong points; Assumptions |  | My Opinion Review | 2 w |  |  |  |  | My Opinion
|  | First Literature Review writing | 5w |  |  |  | 1st Literature Review writing
|  | 1st Rep Liter Review Power Point | 1 w | [7 empty] | 1st Rep Liter Review Power Point
System Manager |  | 1st Report Presentation | Milestone | [9 empty] | 1st Report Presentation
Doc Writter |  | Introduction | 3 w | Introduction
Problem / Hyp. / Context |  | What is investigated | 1 w | What
Why to solve |  | Motivation | 1 w | Motivation
Assumptions ours |  | Parameters / Limitations | 2 w |  | Parameters
Method ours |  | Approach | 2 w |  | Approach
Content Report / Originality |  | Roadmap project | 2 w |  | Roadmap
|  | Introduction Paragraphs | DOC |  |  | Introduction Paragraphs
Project Manager |  | Project Planning | 3 w | Project Planning
|  | Method Selection | 1 w | Method Selection
|  | Master Schedule | 2 w |  | Master Sch
|  | Tasks Schedule | 2 w |  | Tasks Sch
|  | Project Schedule | DOC |  |  | Project Schedule
Requirements Analist |  | System Requirements | 2 w |  |  |  | System Req.
|  | Non-Functional Requirements | 1 w |  |  |  | Non-Functional Requirements
|  | Functional Requirements | 1 w |  |  |  |  | Functional Requirements
|  | System Requirements Doc | Milestone |  |  |  |  | System Requirements Doc
Arhitecture Designer |  | System Design | 4 w |  |  |  |  | System Design
|  | Conceptual Design | 2 w |  |  |  |  | Conceptual
|  | Structure Architecture | 1 w |  |  |  |  | Structure Architecture
|  | Use Case Diagram | 1 w |  |  |  |  | Use Case Diagram
|  | Classes Diagram | 1 w | [5 empty] | Classes Diagram
|  | Components Diagram | 1 w | [5 empty] | Components Diagram
|  | Sequence Diagram | 1 w | [5 empty] | Sequence Diagram
|  | Activity Diagram | 1 w | [5 empty] | Activity Diagram
|  | Concrete Modeling | 2 w | [6 empty] | Concrete
|  | System Architecture Doc | Milestone | [7 empty] | System Architecture Doc
System Developer |  | System Development | 5 w | [8 empty] | System Development
|  | Code Data Bases | 1 w | [8 empty] | Code Data Bases
|  | Program Coding | 3 w | [9 empty] | Program Coding
|  | GUI | 3 w | [9 empty] | GUI
Quality Assurance Tester |  | Testing Planning / Coding | 2 w | [17 empty] | Testing Planning / Coding
|  | Testing Analysis/ Debugging | 1 w | [18 empty] | Testing Analysis/ Debugging
|  | System Executable | Milestone | [18 empty] | System Executable
Quality Assurance Tester |  | Results Analysis | 2 w | [19 empty] | Results Analysis
|  | Charts / Statistic | 1 w | [19 empty] | Charts / Statistic
|  | Results Interpretation Doc | 1 w |  | 360 h | Option 1: without working in Holiday | [17 empty] | Results Interpretation Doc
Doc Writter |  | Writing Project Report | 5 w |  | 20 w…360 h : 20 w =18 h/w…18h : 5 days = 3.6 h / day…5 days per week | [19 empty] | Writing Project Report
|  | Abstract / Etics | 1 w |  | M | T | W | T | F | S | S | [13 empty] | Abstract / Etics
|  | Table of Contents | 1 w |  | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 18 h | [12 empty] | Table of Contents
|  | Problem Description / Analysis | 1 w |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 18 h | [12 empty] | Problem Description / Analysis
|  | Method / Planning | 1 w | [8 empty] | too much | [12 empty] | Method / Planning
|  | Design & Implementation | 1 w | [22 empty] | Design & Implementation
|  | Verification / Validation each stage | 1 w |  | 360 h | Option 2: 2w working in each winter / spring Holiday | [19 empty] | Verification / Validation each stage
|  | Tools to support development process | 1 w |  | 24 w…360 h : 24 w =15 h/w…15h : 5 days = 3 h / day…5 days per week | [20 empty] | Tools to support development process
|  | Critical evaluation of project (decisions, lessons learned, production process, evaluation outcome) | 1 w |  | M | T | W | T | F | S | S | [15 empty] | Critical evaluation of project
|  | Conclusion | 1 w |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 15 h | [15 empty] | Conclusion
|  | References | 1 w |  | 2 | 2 | 2 | 3 | 3 | 3 | 0 | 15 h | [15 empty] | References
|  | Appendices | 1 w | [8 empty] | better | [15 empty] | Appendices
System Manager |  | Final Project Report Doc | Milestone | [24 empty] | Final Project Report Doc
Doc Writter |  | Final Report Power Point | 2 w | [29 empty] | Final Report Power Point
System Manager |  | Final Presentation | Milestone | [30 empty] | Final Presentation
|  | Review / Update / Maintain System Operation | 18 w | Review / Update / Maintain System Operation
|  | Selection Methods / Tehniques / Tools | 14 w | Selection Methods / Tehniques / Tools
|  | Printed and Executable Doc Control | 18 w | Printed and Executable Doc Control